## CO__VOID
|  |  |  | Date: |  | 2021-08-25
|  |  |  | Project Number: |  | 1349
|  |  |  | Change Order No.: |  | 1
|  |  |  | General Contractor: |  | Uprite Construction
|  |  |  | Project Name: |  | Amazon - Dublin
5160 Hacienda Drive
Dublin, CA 94568
1240 N 9th Street Suite 3, Modesto CA, 95350 ¦ PHONE: (209) 492-9346 ¦ FAX: (209) 579-1227
DESCRIPTION OF WORK
Framing and patching drywall throughout the building per superintendent request.
| Description | Quantity | Cost | Cycle |  | Subtotal
EQUIPTMENT
Scissor Lifts (3) |  | 2 | 3300 | Month |  | 6600
[5 empty] | Total | 6600
MATERIAL
4x12 Drywall 5/8" |  | 60 | 21 | EA. |  | 1260
Taping Mud |  | 48 | 42.5 | Box |  | 2040
Hot Mud |  | 20 | 13.5 | Bag |  | 270
Fasteners |  | 4 | 85 | Box |  | 340
3 5/8" x 10' Metal Stud 20 Gauge |  | 200 | 16 | EA. |  | 3200
[5 empty] | Total | 7110
LABOR
Man Hours |  | 980 | 85 | Hours |  | 83300
[5 empty] | Total | 83300
|  |  |  | 10% Mark Up | 9701
|  |  | GRAND TOTAL |  | 106711
Described additional work is to be performed under the same conditions as specified in original contract
Date: _____________________________________________
Approved by: _______________________________________
Print Name: ________________________________________

## CO2
|  |  |  | Date: |  | 2021-12-28
|  |  |  | Project Number: |  | 1349
|  |  |  | Change Order No.: |  | 2
|  |  |  | General Contractor: |  | Uprite Construction
|  |  |  | Project Name: |  | Amazon - Dublin
5160 Hacienda Drive
Dublin, CA 94568
1240 N 9th Street Suite 3, Modesto CA, 95350 ¦ PHONE: (209) 492-9346 ¦ FAX: (209) 579-1227
DESCRIPTION OF WORK
Adding corrugated metal to skylights.
| Description | Quantity | Cost | Cycle |  | Subtotal
EQUIPTMENT
Scissor Lift |  | 1 | 250 | Week |  | 250
[5 empty] | Total | 250
MATERIAL
Corrugated Metal |  | 20 | 42.5 | Sheet |  | 850
1 1/2 x 1 1/2 Steel Angle |  | 18 | 8.3 | EA. |  | 149.4
Fasteners |  | 1 | 85 | Box |  | 85
[5 empty] | Total | 1084.4
LABOR
Man Hours |  | 40 | 85 | Hours |  | 3400
[5 empty] | Total | 3400
|  |  |  | 10% Mark Up | 473.44
|  |  | GRAND TOTAL |  | 5207.84
Described additional work is to be performed under the same conditions as specified in original contract
Date: _____________________________________________
Approved by: _______________________________________
Print Name: ________________________________________

## CO1
|  |  |  | Date: |  | 2021-10-21
|  |  |  | Project Number: |  | 1349
|  |  |  | Change Order No.: |  | 1
|  |  |  | General Contractor: |  | Uprite Construction
|  |  |  | Project Name: |  | Amazon - Dublin
5160 Hacienda Drive
Dublin, CA 94568
1240 N 9th Street Suite 3, Modesto CA, 95350 ¦ PHONE: (209) 492-9346 ¦ FAX: (209) 579-1227
DESCRIPTION OF WORK
Installation of 4x10 timbers with clips around all HVAC units.
| Description | Quantity | Cost | Cycle |  | Subtotal
EQUIPTMENT
Fork Lift |  | 1 | 5000 | Month |  | 5000
[5 empty] | Total | 5000
MATERIAL
4x12 DF |  | 500 | 36 | EA. |  | 18000
L50 Clips |  | 1 | 800 | Bulk |  | 800
Fasteners |  | 1 | 400 | Bulk |  | 400
[5 empty] | Total | 19200
LABOR
Man Hours |  | 235 | 85 | Hours |  | 19975
[5 empty] | Total | 19975
|  |  |  | 10% Mark Up | 4417.5
|  |  | GRAND TOTAL |  | 48592.5
Described additional work is to be performed under the same conditions as specified in original contract
Date: _____________________________________________
Approved by: _______________________________________
Print Name: ________________________________________

## LOG
Amazon - Dublin
Description | Status | Performed? | Date Sent | GC Notice 2 | GC Notice 3 | CO # | T&M # | Invoice | GC # | TOTALS | Amnt Approved | Difference | Comments
VOID_CO1: Framing and patching drywall throughout the building per superintendent request. | VOID | 0 | 2021-08-25 |  |  | VOID |  |  |  | 106711 | VOID | 0 | Work will be tracked by T&M Basis.
tnm1: Repaired framing and drywall. | sent | 1 | 2021-10-14 | 2021-11-19 | 2021-12-07 |  | 1 |  |  | 2376 |  | 0
tnm2: Repaired framing and drywall continued. | sent | 1 | 2021-10-14 | 2021-11-19 | 2021-12-07 |  | 2 |  |  | 654.5 |  | 0
tnm3: Greenline repair framing and drywall continued. | sent | 1 | 2021-10-14 | 2021-11-19 | 2021-12-07 |  | 3 |  |  | 2376 |  | 0 | Greenline = gridline? :\
tnm4: End greenline. Repaired framing and drywall continued. | sent | 1 | 2021-10-14 | 2021-11-19 | 2021-12-07 |  | 4 |  |  | 2244 |  | 0 | Greenline = gridline? :\
tnm5: Drywall repair and framing. | sent | 1 | 2021-10-14 | 2021-11-19 | 2021-12-07 |  | 5 |  |  | 3740 |  | 0 | Greenline = gridline? :\
tnm6: Repaired framing and drywall cont. Exterior for the windows 24 1/2 x 24 1/2. | sent | 1 | 2021-10-14 | 2021-11-19 | 2021-12-07 |  | 6 |  |  | 4488 |  | 0
tnm7: Demolition of drywall at electrical room. | sent | 1 | 2021-10-14 | 2021-11-19 | 2021-12-07 |  | 7 |  |  | 2332 |  | 0 | Charged 1 Scissorlift for September (Need to charge 2 more for September)
tnm8: Remove drywall at exhaust wall ducting. 8 sections. | sent | 1 | 2021-10-14 | 2021-11-19 | 2021-12-07 |  | 8 |  |  | 1496 |  | 0
tnm9: Cont. with framing and drywall, clean up at roof | sent | 1 | 2021-10-14 | 2021-11-19 | 2021-12-07 |  | 9 |  |  | 2057 |  | 0
tnm10: Removed framing and drywall. Cleaned up afterwards. | sent | 1 | 2021-10-19 | 2021-11-19 | 2021-12-07 |  | 10 |  |  | 1402.5 |  | 0
tnm11: Fire taping around the perimeter walls. | sent | 1 | 2021-10-22 | 2021-11-19 | 2021-12-07 |  | 11 |  |  | 4037 |  | 0
tnm12: Fire taping on the perimeter walls, continued. | sent | 1 | 2021-10-22 | 2021-11-19 | 2021-12-07 |  | 12 |  |  | 1496 |  | 0
tnm13: Taping in the perimeter walls and electrical room. | sent | 1 | 2021-10-22 | 2021-11-19 | 2021-12-07 |  | 13 |  |  | 1496 |  | 0
tnm14: Taping in the perimeter walls and electrical room. Plus clean up. | sent | 1 | 2021-10-22 | 2021-11-19 | 2021-12-07 |  | 14 |  |  | 1496 |  | 0
CO1: Installation of 4x10 timbers with clips around all HVAC units. | sent | 1 | 2021-10-21 | 2021-11-19 | 2021-12-07 | 1 |  |  |  | 48592.5 |  | 0 | Was sent to only Kevin
tnm15: Taping in perimeter walls, cont. | sent | 1 | 2021-10-26 | 2021-11-19 | 2021-12-07 |  | 15 |  |  | 1496 |  | 0
tnm16: Taping around the perimeter walls | sent | 1 | 2021-10-29 | 2021-11-19 | 2021-12-07 |  | 16 |  |  | 4488 |  |  | Sent a reminder for payment on 11/5/2021
tnm17: Taping the perimeter walls | sent | 1 | 2021-11-05 | 2021-11-19 | 2021-12-07 |  | 17 |  |  | 7480
tnm18: Taping at wall #14 and green line. | sent | 1 | 2021-11-12 | 2021-11-19 | 2021-12-07 |  | 18 |  |  | 4488 |  |  | Sent another reminder for payment on 11/12/2021
tnm19: Repaired framing & drywall greenland #1 | sent | 1 | 2021-11-16 | 2021-11-19 | 2021-12-07 |  | 19 |  |  | 16357 |  |  | Charged 3 Scissorlifts for October
tnm20: Repaired framing, drywall, taping | sent | 1 | 2021-11-19 | 2021-11-19 | 2021-12-07 |  | 20 |  |  | 14212
CO#2 Adding corrugated metal to skylights | sent | 1 | 2021-12-28 |  |  | 2 |  |  |  | 5207.84
tnm21: Removed the electrical room started framing the wall and hanged the drywall. | sent | 1 | 2022-01-11 |  |  |  | 21 |  |  | 2244
tnm22: Started skylights with the corrugated and removed the wall and framed, patched the holes of the lights outside. | void | 0 | 2022-01-11 |  |  |  | 22 |  |  | 2244 |  | 0 | Same thing as CO#2
tnm23: Continued the skylights with the corrugated metal. Removed the wall and framing. Patched the holes of the lights outside. | void | 0 | 2022-01-11 |  |  |  | 23 |  |  | 1496 |  | 0 | Same thing as CO#2
tnm24: Taping in the perimeter drywall. | sent | 1 | 2022-01-11 |  |  |  | 24 |  |  | 1496 |  | 0
tnm25: Taping in the perimeter drywall, continued. | sent | 1 | 2022-01-11 |  |  |  | 25 |  |  | 1496 |  | 0
tnm26: Patch work around light fixtures | sent | 1 | 2022-01-12 |  |  |  | 26 |  |  | 6751.8 |  | 0 | Next Tag charge scissorlift twice
0
0
0
0
0
CHANGE ORDER TOTALS | [6 empty] | 146000.14 |  |  |  | 0
Project Manager | Nathan Gunderson |  |  |  | nathan.gunderson@upriteco.com
Project Engineer
Superintendent | Kyle Howes |  |  |  | kyle.howes@upriteco.com
Project Accountant | Tracy Tillet |  |  |  | tracy.tillet@upriteco.com
GSC Project # | 1349 & 1353 | [6 empty] | 949-877-8877
Job Location | 5160 Hacienda Drive |  |  | Dublin, CA 94568
| Brad Krouse |  |  |  | brad.krouse@upriteco.com

## tnm1
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-09-30
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 1
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Efrain Fernandez | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Yimi Sandoval | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
3 |  |  | HRS: 0
4 |  |  | HRS: 0
5 |  |  | HRS: 0
6 |  |  | HRS: 0
7 |  |  | HRS: 0
8 |  |  | HRS: 0
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
| 4x12 Drywall 5/8" |  | W: 30; S/S: 21; RATE: 630
| Taping Mud Box |  | S/S: 42.5; RATE: 0
| Hot Mud Bag |  | S/S: 13.5; RATE: 0
| Box of Fasteners |  | W: 2; S/S: 85; RATE: 170
| 5/8" x 10' Metal Stud 20 GA |  | S/S: 16; RATE: 0
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 800
[8 empty] | Total Labor |  | 1360
[7 empty] | + |  | 10% Mark UP | 216
[7 empty] | Grand Total: |  |  | 2376
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Repaired framing and drywall.

## tnm2
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-01
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 2
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Efrain Fernandez | F: 2; HRS: 2; RATE: 85; TOTAL: 170
2 | Framer | Yimi Sandoval | F: 2; HRS: 2; RATE: 85; TOTAL: 170
3 | Framer | Jose Barajas | F: 3; HRS: 3; RATE: 85; TOTAL: 255
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2 |  |  | RATE: 0
3 |  |  | RATE: 0
4 |  |  | RATE: 0
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 595
[7 empty] | + |  | 10% Mark UP | 59.5
[7 empty] | Grand Total: |  |  | 654.5
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Repaired framing and drywall continued.

## tnm3
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-05
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 3
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Efrain Fernandez | T: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Yimi Sandoval | T: 8; HRS: 8; RATE: 85; TOTAL: 680
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 | 4x12 Drywall 5/8" |  | W: 30; S/S: 21; RATE: 630
2 | Taping mud box |  | S/S: 42.5; RATE: 0
3 | hot mud bag |  | S/S: 13.5; RATE: 0
4 | Box of Fasteners |  | W: 2; S/S: 85; RATE: 170
5 | 5/8" x 10' Metal Stud 20 GA |  | S/S: 16; RATE: 0
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 800
[8 empty] | Total Labor |  | 1360
[7 empty] | + |  | 10% Mark UP | 216
[7 empty] | Grand Total: |  |  | 2376
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Greenline repair framing and drywall continued.

## tnm4
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-06
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 4
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Jose Vicente Morales | W: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Enrique Naranjo | W: 8; HRS: 8; RATE: 85; TOTAL: 680
3 | Framer | Noe Lagos | W: 8; HRS: 8; RATE: 85; TOTAL: 680
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2 |  |  | RATE: 0
3 |  |  | RATE: 0
4 |  |  | RATE: 0
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 2040
[7 empty] | + |  | 10% Mark UP | 204
[7 empty] | Grand Total: |  |  | 2244
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
End greenline. Repaired framing and drywall continued.

## tnm5
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-07
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 5
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Jose Vicente Morales | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Enrique Naranjo | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
3 | Framer | Noe Lagos | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
4 | Framer | Efrain Fernandez | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
5 | Framer | Yimi Sandoval | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2 |  |  | RATE: 0
3 |  |  | RATE: 0
4 |  |  | RATE: 0
5 |  |  | RATE: 0
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 3400
[7 empty] | + |  | 10% Mark UP | 340
[7 empty] | Grand Total: |  |  | 3740
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Drywall repair and framing.

## tnm6
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-08
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 6
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Enrique Naranjo | F: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Jose Vicente Morales | F: 8; HRS: 8; RATE: 85; TOTAL: 680
3 | Framer | Efrain Fernandez | F: 8; HRS: 8; RATE: 85; TOTAL: 680
4 | Framer | Yimi Sandoval | F: 8; HRS: 8; RATE: 85; TOTAL: 680
5 | Framer | Oscar Dominguez | F: 8; HRS: 8; RATE: 85; TOTAL: 680
6 | Framer | Noe Lagos | F: 8; HRS: 8; RATE: 85; TOTAL: 680
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2 |  |  | RATE: 0
3 |  |  | RATE: 0
4 |  |  | RATE: 0
5 |  |  | RATE: 0
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 4080
[7 empty] | + |  | 10% Mark UP | 408
[7 empty] | Grand Total: |  |  | 4488
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Repaired framing and drywall continued. Exterior for the windows 24 1/2 x 24 1/2.

## tnm7
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-09-28
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 7
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Ignacio Gonzales | W: 6; HRS: 6; RATE: 85; TOTAL: 510
2 | Framer | Eduardo Tejeda | W: 6; HRS: 6; RATE: 85; TOTAL: 510
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 | Scissorlift 26' (Month) |  | W: 1; S/S: 1100; RATE: 1100
2
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 1100
[8 empty] | Total Labor |  | 1020
[7 empty] | + |  | 10% Mark UP | 212
[7 empty] | Grand Total: |  |  | 2332
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Demolition of drywall at electrical room.

## tnm8
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-08-30
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 8
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Ignacio Gonzales | M: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Eduardo Tejeda | M: 8; HRS: 8; RATE: 85; TOTAL: 680
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 1360
[7 empty] | + |  | 10% Mark UP | 136
[7 empty] | Grand Total: |  |  | 1496
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Remove drywall at exhaust wall ducting. 8 sections.

## tnm9
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-11
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 9
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Efrain Fernandez | M: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Yimi Sandoval | M: 8; HRS: 8; RATE: 85; TOTAL: 680
3 | Framer | Luis Rosales | T: 2; HRS: 2; RATE: 85; TOTAL: 170
4 | Framer | Jose G B | T: 2; HRS: 2; RATE: 85; TOTAL: 170
5 | Framer | Oscar Dominguez | T: 2; HRS: 2; RATE: 85; TOTAL: 170
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 1870
[7 empty] | + |  | 10% Mark UP | 187
[7 empty] | Grand Total: |  |  | 2057
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Repaired framing and drywall, clean up at roof.

## tnm10
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-15
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 10
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Omar Bautista | F: 6; HRS: 6; RATE: 85; TOTAL: 510
2 | Framer | Oscar Dominguez | F: 6; HRS: 6; RATE: 85; TOTAL: 510
3 | Framer | Jose G Guerra | F: 3; HRS: 3; RATE: 85; TOTAL: 255
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 1275
[7 empty] | + |  | 10% Mark UP | 127.5
[7 empty] | Grand Total: |  |  | 1402.5
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Removed framing and drywall. Cleaned up afterwards.

## tnm11
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-19
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 11
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Omar Bautista | T: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Victor Lopes | T: 8; HRS: 8; RATE: 85; TOTAL: 680
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 | Taping mud (Box) |  | W: 48; S/S: 42.5; RATE: 2040
2 | Hot mud |  | W: 20; S/S: 13.5; RATE: 270
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 2310
[8 empty] | Total Labor |  | 1360
[7 empty] | + |  | 10% Mark UP | 367
[7 empty] | Grand Total: |  |  | 4037
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Fire taping around the perimeter walls.

## tnm12
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-20
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 12
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Omar Bautista | W: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Victor Lopes | W: 8; HRS: 8; RATE: 85; TOTAL: 680
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1
2
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 1360
[7 empty] | + |  | 10% Mark UP | 136
[7 empty] | Grand Total: |  |  | 1496
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Fire taping on the perimeter walls, continued.

## tnm13
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-21
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 13
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Omar Bautista | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Victor Lopes | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1
2
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 1360
[7 empty] | + |  | 10% Mark UP | 136
[7 empty] | Grand Total: |  |  | 1496
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Taping in the perimeter walls and electrical room.

## tnm14
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-22
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 14
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Oswaldo Lopes | F: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Victor Lopes | F: 8; HRS: 8; RATE: 85; TOTAL: 680
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1
2
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 1360
[7 empty] | + |  | 10% Mark UP | 136
[7 empty] | Grand Total: |  |  | 1496
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Taping in the perimeter walls and electrical room. Plus clean up.

## tnm15
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-10-26
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 15
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Oswaldo Lopes | T: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Victor Lopes | T: 8; HRS: 8; RATE: 85; TOTAL: 680
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1
2
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 1360
[7 empty] | + |  | 10% Mark UP | 136
[7 empty] | Grand Total: |  |  | 1496
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Taping in the perimeter walls, continued.

## tnm16
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 10/27 - 10/29/2021
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 16
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Oswaldo Lopes |  |  | 8 | 8 | 8 |  | 24 | 85 | 2040
2 | Framer | Victor Lopes |  |  | 8 | 8 | 8 |  | 24 | 85 | 2040
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1
2
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 4080
[7 empty] | + |  | 10% Mark UP | 408
[7 empty] | Grand Total: |  |  | 4488
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Taping around the perimeter walls.

## tnm17
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 11/1/2021 - 11/5/2021
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 17
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Victor Lopes | 8 | 8 | 8 | 8 | 8 |  | 40 | 85 | 3400
2 | Framer | Oswaldo Lopes | 8 | 8 | 8 | 8 | 8 |  | 40 | 85 | 3400
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1
2
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 6800
[7 empty] | + |  | 10% Mark UP | 680
[7 empty] | Grand Total: |  |  | 7480
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Taping the perimeter walls.

## tnm18
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 11/8/2021 & 11/9/2021
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 18
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Omar Bautista | T: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Ignacio Gonzales | T: 8; HRS: 8; RATE: 85; TOTAL: 680
3 | Framer | Victor Lopes | M: 8; T: 8; HRS: 16; RATE: 85; TOTAL: 1360
4 | Framer | Oswaldo Lopes | M: 8; T: 8; HRS: 16; RATE: 85; TOTAL: 1360
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1
2
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 4080
[7 empty] | + |  | 10% Mark UP | 408
[7 empty] | Grand Total: |  |  | 4488
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Taping at wall #14 and green line. Repaired framing and drywall. Taped around the building.

## tnm19
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 11/10/2021 - 11/12/2021
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 19
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Omar Bautista |  |  | 8 | 8 | 8 |  | 24 | 85 | 2040
2 | Framer | Ignacio Gonzales |  |  | 8 | 8 | 8 |  | 24 | 85 | 2040
3 | Framer | Jose G Guerra | W: 6; HRS: 6; RATE: 85; TOTAL: 510
4 | Taping | Victor Lopes |  |  | 8 | 8 | 8 |  | 24 | 85 | 2040
5 | Taping | Oswaldo Lopes |  |  | 8 | 8 | 8 |  | 24 | 85 | 2040
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 | 3 5/8" x 10' Metal Stud 20 Gauge |  | W: 200; S/S: 16; RATE: 3200
2 | Scissorlift 26' |  | W: 3; S/S: 1000; RATE: 3000
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 6200
[8 empty] | Total Labor |  | 8670
[7 empty] | + |  | 10% Mark UP | 1487
[7 empty] | Grand Total: |  |  | 16357
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Repaired framing and drywall at greenland #1 and A. Taped around the building.

## tnm20
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 11/15 - 11/19/2021
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 20
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Omar Bautista | 8 | 8 | 8 | 8 |  |  | 32 | 85 | 2720
2 | Framer | Ignacio Gonzales | 8 | 8 | 8 | 8 |  |  | 32 | 85 | 2720
3 | Taping | Victor Lopes | 8 | 8 | 8 | 8 | 8 |  | 40 | 85 | 3400
4 | Taping | Oswaldo Lopes | 8 | 8 | 8 | 8 | 8 |  | 40 | 85 | 3400
5 | Taping | Ana Zavala | F: 8; HRS: 8; RATE: 85; TOTAL: 680
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2 |  |  | RATE: 0
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 12920
[7 empty] | + |  | 10% Mark UP | 1292
[7 empty] | Grand Total: |  |  | 14212
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Repaired framing, drywall, and taping. Locations include break room, training room, lobby, and mother's room.

## tnm21
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-12-27
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 21
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Jose G Guerra | M: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Jose Luis | M: 8; HRS: 8; RATE: 85; TOTAL: 680
3 | Taping | Gilberto Sandoval | M: 8; HRS: 8; RATE: 85; TOTAL: 680
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2 |  |  | RATE: 0
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 2040
[7 empty] | + |  | 10% Mark UP | 204
[7 empty] | Grand Total: |  |  | 2244
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Removed the electrical room started framing the wall and hanged the drywall.

## tnm22
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-12-28
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 22
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Erick Hernandez | T: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Jose G Guerra | T: 8; HRS: 8; RATE: 85; TOTAL: 680
3 | Framer | Ignacio Gonzales | T: 8; HRS: 8; RATE: 85; TOTAL: 680
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2 |  |  | RATE: 0
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 2040
[7 empty] | + |  | 10% Mark UP | 204
[7 empty] | Grand Total: |  |  | 2244
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Started skylights with the corrugated and removed the wall and framed, patched the holes of the lights outside.

## tnm23
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2021-12-29
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 23
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Framer | Jose G Guerra | W: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Framer | Luis Rosales | W: 8; HRS: 8; RATE: 85; TOTAL: 680
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2 |  |  | RATE: 0
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 1360
[7 empty] | + |  | 10% Mark UP | 136
[7 empty] | Grand Total: |  |  | 1496
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Continued the skylights with the corrugated metal. Removed the wall and framing. Patched the holes of the lights outside.

## tnm24
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 12/29/2021 - 12/30/2021
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 24
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Taping | Victor Lopes | W: 8; TH: 8; HRS: 16; RATE: 85; TOTAL: 1360
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2 |  |  | RATE: 0
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 1360
[7 empty] | + |  | 10% Mark UP | 136
[7 empty] | Grand Total: |  |  | 1496
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Taping in the perimeter drywall.

## tnm25
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 1/3/2022 - 1/4/2022
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 25
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Taping | Victor Lopes | M: 8; T: 8; HRS: 16; RATE: 85; TOTAL: 1360
3
4
5
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 |  |  | RATE: 0
2 |  |  | RATE: 0
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 0
[8 empty] | Total Labor |  | 1360
[7 empty] | + |  | 10% Mark UP | 136
[7 empty] | Grand Total: |  |  | 1496
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Taping in the perimeter drywall, continued.

## tnm26
ADDITIONAL WORK AUTHORIZATION FORM
| General Contractor |  | Job Name | [5 empty] | Date
| Uprite Construction Corporation |  | Amazon - Dublin | [5 empty] | 2022-01-06
| Street |  | Job Address | [5 empty] | Job No.
| 2211 Michelson Drive, Suite 210 |  | 5160 Hacienda Drive | [5 empty] | 1349
| City / State |  | City/State | [5 empty] | T&M #
| Irvine, CA 92612 |  | Dublin, CA 94568 | [5 empty] | 26
Description:
Labor
| Occupation | Employee Name | M | T | W | TH | F | S/S | HRS | RATE | TOTAL
1 | Taper | Jose Luis Rosales | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
2 | Taper | Omar Bautista | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
3 | Taper | Jose Gabriel Guerra | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
4 | Taper | Uriel Barajas | TH: 8; HRS: 8; RATE: 85; TOTAL: 680
5 | Supervisor | Erick Hernandez | TH: 4; HRS: 4; RATE: 85; TOTAL: 340
6
7
8
Material/Equipment
| Item |  | W: Quantity; S/S: Unit Price; RATE: Total
1 | Scissorlift 26' |  | W: 3; S/S: 1000; RATE: 3000
2 | 4x8 Dens Glass 5/8" |  | W: 3; S/S: 26; RATE: 78
3
4
5
6
7
8
9
10
[5 empty] | Total Material/Equipment |  |  |  |  | 3078
[8 empty] | Total Labor |  | 3060
[7 empty] | + |  | 10% Mark UP | 613.8
[7 empty] | Grand Total: |  |  | 6751.8
Above additional work to be performed under same conditions as specified in original contract unless otherwise stipulated.
| Approved By: ___________________________________ |  | HRS: Date:______________
Signature: ______________________________________
Contractor Signature
1240 N 9th Street Suite 3, Modesto, CA 95350 ¦ Office: (209)492-9346 ¦ Fax: (209) 579-1227
Patch work around the light fixtures.